## Open Items
Type | Open Items | Action Item | Blocking | Status | Team | Target Date | Assigned to | Comments
Discussion | Super user meeting outcomes to be discussed and aligned |  |  | Closed | All | 2021-11-05 | Olivier,Ankita
Action | Bespoke Fields for germany move to some other Infotype | Analyze and see if this is possible and which Infotype |  | Closed | Tenneco | 2021-11-16 | Simon/Becky | Only HPC uses these 3 Fields Hyp Headcnt SubAccnt Reports To Hyperion Code 11/16 : Becky confirmed the 3 fields will be moved to a different Infotype 9003.
Execution | TELNO South Africa from 0006 to 0105 |  |  | Execution | IBM |  | Ankita/Kris | Legal reporting is not accepting + , no special characters
Execution | Postal code not needed IT 0009 |  |  | Execution | IBM |  | Kris | Send Blank
Discussion | 4 Administrator fields need to be added on EC for IT 0001(Administrator Group Administrator for Time Recording Administrator for Payroll Administrator for HR Master Data) |  |  | Closed | All | 2021-11-05 | Ankita/Kris/Olivier | Do we need for all Countries
Execution | Emp Grp 5 is needed for specific Location | Ankita has to add the Value 5 in EC |  | Closed | IBM | 2021-11-05 | Ankita/Kris | For Termination can it be updated manually
Discussion | Cost Center in English |  |  | Closed | Tenneco | 2021-11-05 | Olivier | MIOC Location - New ones will be manually created both in HR and EC
Action | For Location, PA we have 2 types of Texts | Jesseca to send email to Ankita with values |  | Closed | Tenneco | 2021-11-17 | Jesseca | Name and Name2 11/4 Jesseca working on remaaining 25 % whare Name 2 is missing 11/10 10 rows missing , waiting on some people 11/17 All rows have name and Name2 - will be sent today
Discussion | Field and Value Mappiing for VPC |  |  | Closed | All | 2021-11-05 | Simon/Becky/Murali | Need Quick Review, can be copied from HPC
Action | Payment Method IT 0009 | 11/10 Olivier sent the mapping to Ankita | High | Closed | IBM | 2021-11-24 | Ankita | 11/22:Ankita to set it up today 11/24: will be loaded in EC. Identified few common values which needs to be handled in Value mapping. 11/29: Ankita confirmed.
Action | Pay Scale values need to be captured for IT 0008 for the Countries approved | Ankita is going to provide the file format Simon/Murali to send the values in the format shared | No | Closed | IBM | 2021-12-15 | Ankita | 12/14 : Olivier and Ankita met and trying to load the file. PSG and PSL will be loaded tomorrow. 12/15 : PSA and PST are loaded. PSG has an issue. 12/16 : PSG has issues and PSL will be loaded after PSG 12/17 : Complete, Associated rates will be loaded before Unit Testign Starts
Discussion | Location for PS Business Unit Email from Dan |  |  | Closed | All | 2021-11-19 | Olivier / Aravind / Ankita / IAM | What happens when a person moves from CAPT to MPPS or vice versa VPC to H1P Germany, LE Change need termination and Rehire and normally btw systems it will be a LE Change Please work with the team to define the process, and set up a call to review. We need to be able to clearly derive and update mapping if needed. We need to be able to flag cross company employees. This cannot be derived from a larger unity such as BG or BU. Looking forward to the recommendation
Discussion | Cross company employees for GRC |  |  | Hold | All | 2021-11-30 | Olivier / Aravind / Ankita / IAM | How can we identify people that needs access to both CAPT and MPPS For exisiting employee, Main record is in CAPT. Crosscompany record exists in MPPS. Employee moves from CAPT location to MPPS location in EC. What happens to the cross-company ID in MPPS? 11/16 : Will be discussed when GRC team is on board.
Discussion | IT 0008 for 5 Countries | Ankita to send her inputs for India to Olivier |  | Closed | All | 2021-11-05 | Olivier / Ankita | When can we be ready to present to Dan, Germany, Spain completed France not needed Olivier shooting for Tuesday Setup call with Dan for Friday
Discussion | Company Code varies btw FI & HR [HPC] | Check on Concur, Incliding towards using FI Company Codes in EC |  | Closed | Tenneco | 2021-11-05 | Simon | FI CoCds in EC and mapping when sending to HPC Transaction Code - SOLE
Discussion | Company Code varies btw FI & HR from Murali H1P MPPS, 0003 and 9001 | Check on Concur, Incliding towards using FI Company Codes in EC |  | Closed | IBM | 2021-11-15 | Aravind/Ankita | Sent email on 10/27, Aravind to design
Action | Poland muncipality code and county code |  | Very High | Closed | IBM | 2021-12-09 | Ankita | 11/24: Internally meeting to close the item, County code and Municipality code will be updated in EC and other 2 fields Province code and county gus code will be auto populated-ABAP Team to update. 11/30 : EC team checking with Poland Super User, waiting for response 12/6 : Ankita to respond to Poland Users to provide the Information. 12/9 : Config is complete.
Action | 9002 - Latest Employement Global - YA |  |  | Closed | Tenneco |  | Ewa | Can be generated directly in HR from IT 41
Action | Concur related Business Area |  |  | Closed | Tenneco | 2021-11-23 | Becky | 11/22: Meeting scheduled with concur team
Action | Executive Manager |  |  | Closed | All |  |  | Has Reports or Job Level 4 and Up for SAP Concur
Action | EC to HR standard Integration Filter Criteria *country *company code *employee type *employee class |  | No | Closed | Tenneco | 2021-12-15 | Murali ,Jesseca | 12/14: QAD completed Plex team is checking 1 company code as they don’t use any code Murali to get back on missing FI company codes for 4 HR company codes being used by Concur Jesseca working on Personnel area 12/15 : By the EOD today, Company codes will be loaded and Jessical will send the Location file as well. 12/17 : All 232 Company codes have been loaded - we had few conflicts.
Action | ORG Key - IN EC or Integration | Ankita sent email to Olivier Olivier to confirm |  | Closed | Tenneco | 2021-11-18 | Olivier | Mapping provided by ?? 11/16 : Ankita to resend email for confirmation with TEN_OTR
Action | Value Mapping btw EC and HR for all 4 systems Event/Reason mapping |  | Very High | Closed | IBM | 2021-12-14 | Ankita/Olivier | 12/13 : Ankita/Aravind to work offline. And for TBD items will review tomorrow 12/14
Action | Contract Type for all 4 HR systems | Simon sent values to Ankita, Any questions? |  | Closed | IBM | 2021-11-12 | Ankita | for IT 1 and IT 16 Contract type is different
Action | ADP Brazil Fields | Ankita to create PID field in EC |  | Closed | Tenneco | 2021-11-05 | Jesseca | Jesseca to add it to Data Model for Data Migration
Action | BTRTL - Personnel SubArea based on Personnel Area [Location] for all 4 SAP HR systems | Simon to send values to Ankita |  | Closed | Tenneco | 2021-11-05 | Simon/Murali | Values to be updated in EC
Action | Zregion is created in EC | Zregion is created in EC |  | Closed | IBM | 2021-11-05 | Arys/Kris | 3 Regions
Action | Subtypes of IT 0006 Address |  |  | Closed | Tenneco | 2021-11-05 | Tenneco
Action | Wagetypes need to be captured for IT 0008 for the Countries approved | Ankita sent email to Olivier Olivier to confirm | High | Closed | Tenneco | 2021-12-14 | Ankita/Olivier | 12/9 : 99% Complete. 2 Wagetypes for Germany need text. Will be Loaded today 12/13 : Olivier sent the Germany Text. Remaining have been loaded. 12/14 : Completed. Need New frequency 4 weekly Payroll
Action | Company Codes - 3519/3520 - Bretten Not in list Olivier provided V4 |  | Medium | Closed | Tenneco | 2021-11-29 | Olivier | 11/22: Olivier to work on this 11/24: Olivier to discuss with Simon No Active EEs in 3520. Not needed in EC. 3519 - 300 EEs Actives in HPC, PA - DE07 is in the list Olivier sent.
Discussion | Cost Centers for ALL Employees especially not maintianed in 4 HR Systems [Non-SAP Cost Centers] |  |  | Closed | All | 2021-11-19 | Ankita/Aravind/Olivier | Data Migration / Default when replication happens, Its complex and Dan agreed for Phase 2 11/10 Are there defaulting any Cost Centers in 4 SAP HR Systems 11/11 Will discuss with Ankita, Logic needed from Olivier
Discussion | Gdansk - Location - POLAND ( B_XX - 20 to 22 values but when we send to other systems it is converted GDSK ) | Payroll for 1000 EE's, Olivier already contacted Dan on this one. | High | Hold | Tenneco |  | Olivier/Ewa | 21-22 Locations embedded We need to know the logic behind if we can convert GDSK into B_ based on some other field Will be a problem for Recruiting and ONB 2.0 Do not have full information and Olivier planning to visit the site to understand the data 11/10 Dan is checking with HR Director from Business 12/6: Olivier/Ewa to travel to Poland in Jan 2022. 800-1000 EEs
Action | Dynamic Actions to be sent for H1P CAPT | Dynamic Actions to be sent for H1P CAPT |  | Closed | Tenneco | 2021-11-17 | Murali | Discuss the files received , H1P CAPT missing
Action | User Exits to be reviewed | Aravind to send email to Dona |  | Closed | IBM | 2021-11-16 | Aravind
Action | Email from Simon |  |  | closed | IBM |  | Kris / Ankita | Dated 10/27/2021 1:57:00 PM
Action | Identifying Managers | POC to be done |  | Closed | IBM | 2021-11-16 | Kris / Ankita | Need to be tested how TotalTeam Size changes when reportee is assigned To be tracked in Development Plan
Action | Employee Sub Group - Unique-H1P CAPT and MPPS | Simon to send values to Ankita | No | Closed | IBM | 2021-12-15 | Ankita | 12/14: Simon sent the File - Ankita whas the Infoormation 12/15 : Will be loaded today. We had some conflicts and they have been addressed. 12/16 : Loaded into EC. Completed
Action | Infotype Updates per country and per type of employee per system |  |  | closed | IBM | 2021-11-01 | Aravind / Kris
Action | Review Field / Value Mapping Workbooks for any action items in Remarks | Kris has to comeup if there are any open items from workbooks |  | Closed | IBM | 2021-11-16 | Kris
Discussion | Workflow Approvals for FIORI / FI Systems / any downstream systems |  |  | closed | IBM |  | Aravind | Inftype 9001 is used to identify supervisor
Action | Sandbox Access -H1S | Simon/Murali to provide access to Sandbox |  | Closed | Tenneco | 2021-11-05 | Simon/Murali | H1P CAPT after Patching 11/4 We ca nuse but Basis will perform patching
Action | Does Org unit needed if we have to send position for Postiion Title, what happens to PA-OM Sync | POC to be done |  | Closed | IBM | 2021-11-19 | Kris/Aravind/Dona | 11/16 : Waiting on Access in H1S Sandbox 11/17 Simon to check on Dona Access. Ren we are waiting for Cross Company request
Discussion | OM Integration for USA - Design JobCode & Department |  |  | Closed | Tenneco | 2021-11-30 | Murali | 11/30: Murali sent meeting minutes. Will close the item once reviewed 12/1: No OM-PA Integration of USA and Mexico.
Action | Managers to all remaining 3 Systems with Basic Data and Cross Company Employees | Send default values for the managers from other systems |  | closed | Tenneco | 2021-11-22 | Murali/Jesseca/Simon | Default values to be used for IT 0/1/9001 11/18: Simon has a meeting scheduled tomorrow to discuss 11/19: Simon to send the file . 11/22: Aravind sent email with questions .Simon to respond
Action | Supervisor Area | Jesseca to check if this is used or not by Germany | Medium | Closed | Tenneco | 2021-11-29 | Jesseca/Olivier | 11/22: Jesseca sent the data . Olivier to work again based on feedback from Ankita. 11/24: Added to EC only for Germany.
Action | Company Code mapping btw SAP HR and Finance for HPC and VPC |  |  | Closed | IBM | 2021-11-19 | Aravind | Becky sent the latest updates - Aravind to check 11/17 Will review today
Discussion | Skokie - Company Code MP10 moving to EP1 - 2nd or 3rd QTR Meetings |  |  | Closed | Tenneco | 2021-11-16 | Raghu/Murali | Will be handled in Raid Log , Employee will move from MP10 to 1070.
Action | Bank file download | BNKA - Table download from H1P CAPT and MPPS |  | Closed | Tenneco | 2021-11-22 | Simon | HPC, VPC done. H1P numbers are huge 11/16 : Simon working on the H1P MPPS File
Action | cust_subRegion (location) | Added the field in EC |  | Closed | IBM | 2021-11-08 | Ankita | Kris to check if ABAP can pull this information from the location object else field has to be created in Job Information
Action | cust_region (location) | Need to be added to EC |  | Closed | IBM | 2021-11-16 | Ankita | Kris to check if ABAP can pull this information from the location object else field has to be created in Job Information 11/16: Field added in Job Information
Action | Full Name | Simon to check if this is used or not |  | Closed | Tenneco | 2021-11-16 | Simon/Becky, Murali | Simon to check, Country BR and Portugal CNAME 11/16: Confirmed for BR and Portugal
Action | 4 Administrator fields need to be added on EC for IT 0001(Administrator Group Administrator for Time Recording Administrator for Payroll Administrator for HR Master Data) | T526 is the table, Olivier to send it to Ankita | Medium | Closed | IBM | 2021-12-09 | Ankita | 11/22: Jesseca sent the data . Olivier to work again based on feedback from Ankita 11/30: Defaults for all locations. For 4 locations Users will search and override Administrator fields if needed. 12/1 : Ankita to complete the config in EC by 12/2 12/2 : Admin Group is missing for some rows 12/9 : Complete
Action | work location(9001-location) vs Paid location (0001-Personal Area) | Will be discussed in EC Workshops next week | Medium | Closed | IBM | 2021-11-29 | Ankita | Global Assignment - Mulitple Employee #'s going forward New Situation where we might need both locations 11/19: Work in progress, Olivier to give presentation to lynnette/Dan Ankita to create a new field. 11/24: Work location custom field will be added that goes to 9001, Ankita will add the field. 12/1: Added the new field.
Action | REGION_BE Belgium |  |  | Closed | IBM | 2021-11-16 | Ankita | Not needed in the address (IT6)
Action | REGION_CZ Czech |  |  | Closed | IBM | 2021-11-16 | Ankita | Not needed in the address (IT6)
Action | REGION_DK Denmark |  |  | Closed | IBM | 2021-11-16 | Ankita | Not needed in the address (IT6)
Action | REGION_FR France |  |  | Closed | IBM | 2021-11-16 | Ankita | Not needed in the address (IT6)
Action | REGION_GB Region UK |  |  | Closed | IBM | 2021-11-22 | Ankita | 11/22:Ankita to set it up today 11/24: Loaded in EC.
Action | REGION_HU Region Hungary |  |  | Closed | IBM | 2021-11-16 | Ankita | Not needed in the address (IT6)
Action | REGION_IN Region India |  |  | Closed | IBM | 2021-11-16 | Ankita | EC Team to adjust the values, needed in IT6
Action | REGION_RU Region Russia |  |  | Closed | IBM | 2021-11-16 | Ankita | Not needed in the address (IT6)
Action | REGION_SE Region Sweden |  |  | Closed | Tenneco | 2021-11-16 | Olivier | Olivier to check - Values are same but labels are different, IT 0006 - Not Used / Closed
Action | PREFIX Name Prefix |  |  | Closed | Tenneco | 2021-11-16 | Jesseca | EC to create the piclist in EC - Only for Germany 11/16: Jesseca confirmed it is not used
Action | RELIGION Religion | Olivier/Jesseca to confirm that it is not needed in IT 0002 |  | Closed | Tenneco | 2021-11-16 | Jesseca | Discuss with EC team to have 1 global list of religion - Only Germany, IT 0002 & Tax Infotype 11/16: Jesseca confirmed it is not used
Action | Type of Abode, IT 0006 Address |  |  | Closed | IBM | 2021-11-19 | Ankita | EC Team to create the piclist in EC Field added in EC
Action | NAME_FORMAT Name Format Code |  |  | Closed | IBM | 2021-11-16 | Ankita | EC Team Working on it
Action | ADMINISTRATOR_GROUP Administrator Group |  |  | Closed | Tenneco | 2021-11-18 | Jesseca | Simon/Olivier to check active values, Jesseca will send for all 4 Systems - See Row 47
Action | ADMINISTRATOR Administrator |  |  | Closed | Tenneco | 2021-11-18 | Jesseca | Simon/Olivier to check active values, Jesseca will send for all 4 Systems - See Row 47
Action | Create new picklist for region of birth for IT0002 (Personal Information) |  |  | closed | IBM | 2021-11-19 | Ankita | EC Team to create the piclist in EC Field added in EC
Action | H1P MPPS and CAPT send personal area and Personal sub area |  | Medium | Closed | IBM | 2021-11-23 | Ankita | 11/22: File sent by Simon/Jesse. Ankita to load to EC 11/24 : Loaded in EC confirmed by Ankita
Action | NO-SHOW Event/Action [ Legal Reporting needs to be looked into so might be delayed to Phase 2 - Downstream Applications ] | Send email to Dan, Murali to update Gloria and update RAID Log Item | Low | Closed | Tenneco | 2021-12-09 | Murali | Event / Action to be configured in EC/HR Systems, even Portugal needs to be looked into 11/4 Murali to update Gloria and update RAID Log Item 11/10 Murali will schedule the call with Dan 11/16 Murali scheduled the call for Nov 30 12/1: Murali to reschedule the call 12/6: Jess to look at the emai lsent by Ankita. 12/9 : Closing as Raid log item is opened and next step for Murali and Ankita to document how No-Show process will work in EC.
Action | Transports to VDC |  |  | Closed | Tenneco | 2021-11-22 | Simon/Becky
Action | P9001-ZPLANS |  | Very High | Closed | Tenneco |  | Olivier/Simon/Murali | 11/24: Not needed Confirmed by Olivier.
Action | IT 41 mapping and identificaton of date type fields to be created in EC |  | Medium | Closed | Tenneco | 2021-12-14 | olivier | 11/22: File to be reviewed by IBM and has questions 11/24: Decided to go with ABAP Logic to handle the manually entered Date Types. Ewa to work with team to find out if there are any date types that have straight forward logic. 12/1: BADI will accomadate exisiting date types in SAP. Ewa still finding out if we can add logic for any date types 12/6: Olivier to check with Super Users. Ewa on sick leave. 12/10 : Olivier to send logic for some Date Types 12/13 : All unmapped date types from Ewa will be manually maintained in SAP HR
Action | Contingent worker-National ID Optional |  | No | Hold | Tenneco | 2021-12-15 | Simon | 12/14 : Default for USA 9999… , UK Optional , For Poland DOB backwards, - Not Possible in SAP. Currently we are getting the information for Contingent workers. Needs discussion with Lynnette. DOB and Gender is needed for Poland and France. 12/15 : Lynnette scheduled a meeting tomorrow 12/16. 12/16 : Simon to prepare the list of countries where we need real information for Gender, DOB, Nationality and National ID. As a team we will decide the defaults. 1/4 : We need Excel with Per System per Country for all 4 Fields - Gender, DOB, Nationality and National ID. Best Example : We cannot have 999-99-9999 in EC for Multiple Employees s owe need these datails on how they are handled in HR so we can come up with Logic.
Action | Contingent Worker-9001 Infotype |  | Medium | Closed | All |  | Ankita | Did we validate all the fields needed for 9001 12/6 : Validated.
Discussion | Terminated People - Data Migration |  | High | Closed | IBM | 2021-12-09 | Aravind | 12/2 Aravind to send an email to Terry 12/9: Informed during RAID Log call. Olivier to prepare document on what is the period terminated EEs to be integrated In EC- main purpose is how we can handle Rehires.
Discussion | Rehire action for Contingent worker |  |  | Closed |  | 2021-12-14 |  | 12/10 : ZH 50 for H1P MPPS and CAPT. Need to finalize in HPC and VPC
Discussion | Global Assignment Actions on Home Records |  |  | Closed |  | 2021-12-14
Discussion | Bank Information by Personnel Area?? |  |  | Closed |  |  |  | Flag will be added
Action | Enablon code dump |  | High | Closed | Tenneco | 2021-12-14 | Murali | 12/10 : Murali to send dump ZHRLocation with Enablon Code

## Sheet3
Plants | country | CODE | SAP HR | OLD
FM-CAMB-USA | USA | 280 | 1099 | PT-10
FM-BLCK-USA | USA | 201 | 1099 | PT-10
FM-BURL-USA | USA | 283 | 1099 | PT-10
FM-GRNV-USA | USA | 202 | 1099 | PT-10
FM-Athens-USA | USA | 308 | 1099 | PT-10
FM-Skokie-USA | USA | 313 | 1099 | NA
FM-JURMEX | Mexico |  | 3120
FM-JURDISTR | Mexico | 1745 | 3121
FM-PUEB(Bearings) | Mexico | 205 | 3126 | 2022-04-01
FM-JURLUS | Mexico | 5158 | NA | No Employees

## SAP HR Config (hidden)
Open Items | Assigned to | Status | Target Date | Comments
Mexico - New values to be added to SAP HR, List of Region and Municipality,Add Subtypes for IT 105 | Simon & Murali | In Progress |  | New values to be added to SAP HR
Customizing of the New Hire action /Termination …
Roles review to remove the access of ITXXXX coming from EC
Number Interval range review : Pers N°, Position n°
Review the Time Administration for some location
Create the location TEN and others setting for Manager
Remove phone number from IT0006
Create new Private Phone number subtype in IT0006
Review interface SAP ADP US for the phone number from IT0006
Review Legal report from SAP about the contact phone number
Benefits interface review with phone number
Remove the 3 customizing fields from IT0001 on HPC to an other IT
BADI Changes
Program to Delimit the infotypes after termination trigger from EC | Simon & Murali
REGION_GB | Simon & Murali | Simon and Murali to create values in SAP HR |  | All 4 Systems - Kris to send it out
Simon to create CELL subtype in 0105, Sam is working on it | Simon & Murali |  | 2022-01-07 | HDC
Simon/Muralli to create 9018 subtype in 0105 | Simon & Murali |  | 2022-01-07 | H1P-Both, VPC
Simon/Muralli to create 9019 subtype in 0105 | Simon & Murali |  | 2022-01-07 | H1P-Both, VPC
MUNICIPALITY_WS | Simon & Murali | Muralli and Simon to review and create records in SAP HR
Bespoke Fields for germany move to some other Infotype - 9003 for Germany
REGION_IN Region India | Murali/Simon |  |  | 2 States to be added in all HR Systems - Telangana and Ladakh
Tenneco to come up with one Pay Increase Action and Reason as Pay Change in all 4 systems

## check list
All Drop Down values added in HR will need to be captured from now to Go-Live and rechecked before Go-Live | On-Going | Olivier/Jesseca
Data Migration for ADP PAY ID, unique for each EE Jesseca and Terry to map the data from SAP HR to this field in EC with corresponding values
Cross company EE # already exists , transfer to other company where cross company record exists - | In Progress |  | Terminate and send same EMPNO records to cross company

## Sheet1 (hidden)
|  | H1P CAPT |  | LE | Standard Field
LE | ASEX
HPC
|  |  | H* | H-1000 | 1000 | HPC | CAPT
|  |  | C* | C-1000 | 1000 | H1P CAPT | CAPT
|  |  | V* | V-1000 | 1000 | VPC | MPPS
|  |  | M* | M-1000 | 1000 | H1P MPPS | MPPS
|  |  |  | X-1000 |  | No Replciation
M-0003
C-0003
10%
|  |  |  | H-2000 | 2000
|  |  |  | V-2000 | 2000