## Interfaces-CPI
Business Units
S.No | In-Scope | Org | Vendor/System | Interface Name | Middleware | File Format | In/Out | Interface Type | Development Type | Complexity | Phases | Business Owner | Tenneco IT Team | IT Manager | Technical SME | SAP HCM SME | Vendor Manager/Contact | Target/Source | MP | RP | CA | PT | Division | SAP System | MPPS move to Employee Central | CAPT Move to Employee Central | Comments | Target Systems | Country? | Data: Employee / Payroll / Both / Other | Documents : FS or TS or Both Design | Field Mapping | Custom Infotype/Fields | Initial EE Record?? | Change Tracking | Testability Concerns | Sequencing Importance | Data Value Translation | Total Files | File Transmit | Future Dated Rows | Timeliness | Error Handling | Existing Interface | How Executed | AS Comments
1 | Yes | MPPS | Active Directory-MPPS | New Hire/Create a User Termination/Disable User | CPI | Web Service Call | Outbound | T2 | D1 | High | Phase 1 |  | Microsoft Team |  | Lisa Williamson |  |  |  | X | X | X |  | Both | H1P | yes | yes | yes = | AD-MPPS | All | Employee | Yes | Yes | Yes |  |  |  |  | Yes | 1 | [6 empty] | Proposal to merge into 1 AD System. Date ?? 2 USER ID Formats
2 | Yes | MPPS | Active Directory-MPPS | User Principle Name & Work Email Update | CPI | Web Service Call | Inbound | T2 | D1 | Med | Phase 1 |  |  |  | Lisa Williamson |  |  |  | X | X | X |  | Both | H1P | yes | yes | yes = Working Email ID ( Reserved across all systems ) SUBTY 0010 | AD-MPPS | All | Employee | Yes - USERID & EMAILID | Yes | Yes |  |  |  |  | Yes | 1 | [6 empty] | Proposal to merge into 1 AD System. Date ?? 2 USER ID Formats
3 | Yes | CAPT | Active Directory-CAPT | New Hire/Create a User Termination/Disable User | CPI | Web Service Call | Outbound | T2 | D1 | High | Phase 1 |  |  |  | Bina Patel |  |  |  | X | X | X |  | Both | H1P | yes | yes | yes = CAPT currently send to GRC which send the info to AD | AD-CAPT | All | Employee | Yes | Yes | Yes |  |  |  |  | Yes | 1 | [6 empty] | Proposal to merge into 1 AD System. Date ?? 2 USER ID Formats
4 | Yes | CAPT | Active Directory-CAPT | User Principle Name & Work Email Update | CPI | Web Service Call | Inbound | T2 | D1 | Med | Phase 1 |  |  |  | Bina Patel |  |  |  | X | X | X |  | Both | H1P | yes | yes | yes = Working Email ID ( Reserved across all systems ) SUBTY 0010 | AD-CAPT | All | Employee | Yes - USERID & EMAILID | Yes | Yes |  |  |  |  | Yes | 1 | [6 empty] | Proposal to merge into 1 AD System. Date ?? 2 USER ID Formats
5 | Yes | MPPS | SF EC to SAP Master Data H1P MPPS | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | Very High | Phase 1 | [6 empty] | H1P-RP |  |  |  |  | RP | H1P-RP | new
6 | Yes | CAPT | SF EC to SAP Master Data H1P CAPT | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | Very High | Phase 1 | [6 empty] | H1P-CA |  |  |  |  | CA | H1P-CA | new | new
7 | Yes | MP | SF EC to SAP Master Data VPC MP | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | High | Phase 2 | [6 empty] | VPC-MP |  |  |  |  | MP | VPC | new
8 | Yes | PT | SF EC to SAP Master Data HPC PT | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | High | Phase 1 | [6 empty] | HPC-PT |  |  |  |  | PT | HPC | new | new
9 | Yes | MPPS | SF EC to SAP Org Assignment Data H1P MPPS | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | High | Phase 1 | [6 empty] | H1P-RP |  |  |  |  | RP | H1P-RP | new |  | Will be discussed in detail during EC Sessions…if there is need to maintain OM Data.
10 | Yes | CAPT | SF EC to SAP Org Assignment Data H1P CAPT | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | High | Phase 1 | [6 empty] | H1P-CA |  |  |  |  | CA | H1P-CA | new | new | Will be discussed in detail during EC Sessions…if there is need to maintain OM Data.
11 | Yes | MP | SF EC to SAP Org Assignment Data VPC MP | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | High | Phase 2 | [6 empty] | VPC-MP |  |  |  |  | MP | VPC | new |  | Will be discussed in detail during EC Sessions…if there is need to maintain OM Data.
12 | Yes | PT | SF EC to SAP Org Assignment Data HPC PT | Successfactors to SAP HR | CPI | Web Service Call | Outbound | T2 | D3 | High | Phase 1 | [6 empty] | HPC-PT |  |  |  |  | PT | HPC | new | new | Will be discussed in detail during EC Sessions…if there is need to maintain OM Data.
13 | Yes | MPPS | Global Headcount Reporting - MPPS | SAP HANA | CPI | Web Service Call | Outbound | T1 | D1 | High | Phase 3 | Jeroen | [6 empty] | X | X | X |  | Both | H1P | Will be used btw Phase 1 and Phase 2 to feed SAP HANA | yes | Custom Table maintaining Contractor Information, Might be moving to AZURE |  | All | [9 empty] | Multiple, Custom Tables
14 | Yes | CAPT | Global Headcount Reporting - CAPT | SAP HANA | CPI | Web Service Call | Outbound | T1 | D1 | High | Phase 3 | Lucas gong | [6 empty] | X | X | X |  | Both | H1P | Will be used btw Phase 1 and Phase 2 to feed SAP HANA | yes | Custom Table maintaining Contractor Information, Might be moving to AZURE |  | All | [9 empty] | Multiple, Custom Tables
15 | Yes | MPPS | FIORI-MPPS | FIORI NEWHIRES (All ) | CPI | File based | Outbound | T2 | D1 | Med | Phase 2 |  |  |  | Wilfred Poesen/Sam/Antolij |  |  |  | X | X |  |  | DRiV | H1P |  |  | Employee census data for New Hires. | 1 or 2?
16 | Yes | CAPT | FIORI-CAPT | FIORI NEWHIRES (All ) | CPI | File based | Outbound | T2 | D1 | Med | Phase 2 |  |  |  | Zack Cain/Sam/Antolij |  |  |  | X | X |  |  | DRiV | H1P |  |  | Employee census data for New Hires. | 1 or 2?
17 | Yes | MPPS | GRC-MPPS | Security-Governance, Risk, and Compliance | CPI | Web Service | Outbound | T2 | D1 | Very High | Phase 1 |  |  |  | Corina Smith |  |  |  | X | X | [5 empty] | Need to discuss with GRC ( Corina Smith MPPS & Colin Tosh CAPT) | Disabling is happening in GRC, Joel Schoofs |  | All
18 | Yes | CAPT | GRC-CAPT | Security-Governance, Risk, and Compliance | CPI | Web Service | Outbound | T2 | D1 | High | Phase 2 |  |  |  | Colin Tosh | [5 empty] | X | X |  |  |  | Need to discuss with GRC ( Corina Smith MPPS & Colin Tosh CAPT) |  |  | All
19 | Yes | MPPS | Concur-MPPS | Employee master data for concur | CPI | File based | Email | T1 | D1 | High | Phase 2 | Gail Perdew | [6 empty] | X |  | X |  | MP | H1P | yes |  |  |  | ALL
20 | Yes | CAPT | Concur-CAPT | Employee master data for concur | CPI | File based | Email | T1 | D1 | Med | Phase 2 | Molly Wagner |  |  | Carlo Dewit |  |  |  | X |  | X |  | MP | H1P | yes |  |  |  | ALL
21 | Yes | PS(RP) | SAP FI-PTA(1)-MPPS | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Med | Phase 1 |  |  |  | Cristian Berbec (Cristian.Berbec@driv.com) | [11 empty] | Daily
22 | Yes | PS(RP) | SAP FI-TA2(1)-MPPS | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Med | Phase 2 |  |  |  | Cristian Berbec | [11 empty] | Daily
23 | Yes | MP | SAP FI-EP1-MPPS | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 1 |  |  |  | Cristian Berbec | [11 empty] | VPC&H1P
24 | Yes | MP | SAP FI-IP1-MPPS | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 2 |  |  |  | Cristian Berbec
25 | Yes | MP | SAP FI-RP1-MPPS | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 2 |  |  |  | Cristian Berbec | [11 empty] | VPC&H1P
26 | Yes | MP | SAP FI-HP1-MPPS | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 2 |  |  |  | Cristian Berbec
27 | Yes | MP | SAP FI-APW-MPPS | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 2 |  |  |  | Cristian Berbec
28 | Yes |  | QAD-MPPS(non-SAP) | Cost Center from non-SAP FI | CPI | FileBased | Inbound | T2 | D5 | Med | Phase 1 |  |  | Pierre Kok | Cristian Berbec
29 | Yes | CA | SAP FI-PTA(2)-CA | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Med | Phase 1 |  |  |  | Scott Ready | [11 empty] | Daily-Americas
30 | Yes | CA | SAP FI-TA2(2)-CA | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 2 |  |  |  | Thorsten Schimpf | [11 empty] | Daily-EMEA, APAC
31 | Yes | PT | SAP FI-RLP-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Guenther Ulrich | [11 empty] | Uses new GL Solution, We also bring Profit Centers Rings & Liners
32 | Yes | PT | SAP FI-SP1-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Med | Phase 2 |  |  |  | Magdalena Fairclough | [11 empty] | Pistons
33 | Yes | PT | SAP FI-P13-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Ralph Bender | [11 empty] | Bearings
34 | Yes | PT | SAP FI-P14-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Sreenivasan Narangampuram | [11 empty] | Ignition
35 | Yes | PT | SAP FI-INP-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Med | Phase 2 |  |  |  | Sreenivasan Narangampuram | [11 empty] | India
36 | Yes | PT | SAP FI-EE9-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Rafael Englehardt | [11 empty] | GVS
37 | Yes | PT | SAP FI-SGP-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Kannan Sarkalingham | [11 empty] | Coventry
38 | Yes | PT | SAP FI-RP2-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Matt Cramer | [11 empty] | Mexico |  | India
39 | Yes | PT | SAP FI-EP4-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Matt Cramer | [11 empty] | Queretaro
40 | Yes | PT | SAP FI-HE2-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Peter Farren | [11 empty] | Sealings
41 | Yes | PT | SAP FI-FP1-PT | Cost Center from SAP FI | CPI | Web Service | Inbound | T2 | D5 | Low | Phase 3 |  |  |  | Matt Cramer | [11 empty] | Gdansk SSC
42 | Yes | TBD | MFGPRO | Cost Center from non-SAP FI | CPI | FileBased | Inbound | T1 | D1 | Med | Phase 2 |  |  | Pierre Kok | [12 empty] | ??
43 | Yes | TBD | PLEX | Cost Center from non-SAP FI | CPI | FileBased | Inbound | T1 | D1 | Med | Phase 3 |  |  |  | Lidia Newkirk | [11 empty] | Bearings Mexico
44 | Yes | Vendor | ADP Brazil | Employee data to ADP for Brazil payroll | CPI | FileBased | Outbound | T1 | D1 | High | Phase 2 |  |  |  | Simon/Olivier |  |  |  |  | X | X |  | Both | H1P | Yes |  |  |  | Brazil
45 | Yes | Vendor | Enablon-MPPS | Enablon-EHS | CPI | FileBased | Outbound | T1 | D1 | Med | Phase 2 | Lisa Detlefsen(LDetlefsen@driv.com) |  |  | Jayesh Chawda |  |  |  | X | X |  |  | Both | H1P | yes | yes | EHS - Lisa Detlefsen ( Business Contact ) (FLFN.LN@tenneco.com) | Enablon-MPPS | All | Employee | SPEC - Murali | [10 empty] | Daily
46 | Yes | Vendor | Enablon-CAPT | Enablon-EHS | CPI | FileBased | Outbound | T1 | D1 | Med | Phase 3 | Lisa Detlefsen?? |  |  | Jayesh Chawda?? |  |  |  | X | X |  |  | Both | H1P | yes | yes | Check with Marc Mc kee(EHS Director) - He might know the contact | Enablon-CAPT | All | Employee | SPEC - Murali | [10 empty] | Daily
47 | Yes | Vendor | iJET-MPPS | Ijet{Basic Employee Info- Location)- Travel Safe System | CPI | FileBased | Outbound | T1 | D1 | Med | Phase 3 |  |  |  | Anatolij Sipos |  |  |  | X | X |  |  | DRiV | H1P | yes |  | This is to Worldaware who sends travel advisory notifications to place they employee is travelling to. It has employee master data and can be moved. Not used in CAPT | iJET-MPPS | All | Employee | Spec - Murali
48 | Yes | RP | Oracle-RP | ENGR ORACLE | CPI | FileBased | Outbound | T1 | D1 | Med | Phase 3 | Jeroen |  |  | Sam |  |  |  |  | X |  |  | RP | H1P | Yes |  | Employee Master data to Oracle engineering system in EMEA and APAC Simple Query, Maybe for Engineers
49 | TBD | TBD | Certify(T&E) | Certify Census | EDI | text | Outbound | [12 empty] | X |  |  | RP | H1P | yes | NA | no = ?? // Susan Lee or Murali | Only for RP in US | RP-US | Employee | Spec - Murali | [14 empty] | NA for CAPT as it is moved to SAP CONCUR
50 | TBD | TBD | Success Factors | User Directory | PI | text | Outbound |  |  |  |  | Christine Fritz | [6 empty] | X | X |  |  | DRiV | H1P | Will be used btw Phase 1 and Phase 2 to feed Current SF Instance |  |  | MPPS
51 | TBD | TBD | Success Factors | Personal Information | PI | text | Outbound |  |  |  |  | Christine Fritz | [6 empty] | X | X |  |  | DRiV | H1P | Will be used btw Phase 1 and Phase 2 to feed Current SF Instance |  |  | MPPS
52 | TBD | TBD | Success Factors | Background Information | PI | text | Outbound |  |  |  |  | Christine Fritz | [6 empty] | X | X |  |  | DRiV | H1P | Will be used btw Phase 1 and Phase 2 to feed Current SF Instance |  |  | MPPS
53 | TBD | TBD | Success Factors | Position Management | PI | text | Outbound |  |  |  |  | Christine Fritz | [6 empty] | X | X |  |  | DRiV | H1P | Will be used btw Phase 1 and Phase 2 to feed Current SF Instance |  |  | MPPS
54 | TBD | TBD | ADP France | Employee data to ADP for France payroll | [10 empty] | Simon/Olivier | [11 empty] | Project is InProgress |  | France
55 | TBD | TBD | KDR | Skills Matrix Gdansk | [7 empty] | Dorota Hynek |  |  | Simon | [6 empty] | X | PT | HPC | No? | Yes |  |  | Poland
56 | TBD | TBD | AEB Solutions-PT | AEB - Terror profiling | PI | IDOC to file | Outbound |  |  |  |  | Waltraud Weiler |  |  | Simon | [6 empty] | X | PT | HPC | Yes? |  | NEW - Start to build ASAP - Wiesbaden |  | Germany
57 | TBD | TBD | ivocoPro | No spec received yet | PI | IDOC to file | Outbound | [14 empty] | X | PT | HPC | Yes? |  | NEW - Burschied - Time punch data. To start ASAP Simon to check on this one | [18 empty] | Not Needed Simon Confirmed April 29 2021 Strategy Review Call
58 | TBD | TBD | Egencia | Travel Website |  |  | Outbound | [7 empty] | Peter Farren |  |  |  |  | X | X |  | Both | H1P |  |  |  | 4
Deleted
No needs EE Groupings and card nos

## SF Plan
Phase | Interface Name | Owner | Task Description | 2021-07-09 | 2021-07-16 | 2021-07-23 | 2021-07-30 | 2021-08-06 | 2021-08-13 | 2021-08-20 | 2021-08-27 | 2021-09-03 | 2021-09-10 | 2021-09-17 | 2021-09-24 | 2021-10-01 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 2021-10-29 | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18
Phase-1
Pre- Work
|  | Tenneco | Installations(DEV for now), if any [ SAP Add-Ons, Cloud Connecter by Basis ] | bar: 2021-07-09 to 2021-07-30
|  | IBM | SF CPI Middleware and SFTP Setup by IBM | bar: 2021-07-09 to 2021-07-30
|  | Tenneco | Access to Identified systems, wherever required | bar: 2021-07-09 to 2021-07-30
Design
|  | Tenneco | AS-IS Process, FS and TS, Field Mapping & Logic | bar: 2021-07-09 to 2021-07-23
|  | Tenneco and IBM | Design Meetings, TO-BE Process and Approval | bar: 2021-07-30 to 2021-08-20
|  | Tenneco | Identify Test Systems | bar: 2021-07-30 to 2021-08-20
|  | Tenneco and IBM | Finalize Unit Test Strategy | bar: 2021-07-30 to 2021-08-20
Build and Unit Testing
Sender | bar: 2021-08-27 to 2021-12-17
Receiver | bar: 2021-08-27 to 2021-12-17
Phase-2
Pre- Work
|  | Tenneco | Access to Identified systems, wherever required | bar: 2021-08-13 to 2021-08-27
Design
|  | Tenneco | AS-IS Process, FS and TS, Field Mapping & Logic | bar: 2021-08-06 to 2021-08-20
|  | Tenneco and IBM | Design Meetings, TO-BE Process and Approval | bar: 2021-08-27 to 2021-09-17
|  | Tenneco | Identify Test Systems | bar: 2021-08-27 to 2021-09-17
|  | Tenneco and IBM | Finalize Unit Test Strategy | bar: 2021-08-27 to 2021-09-17
Build and Unit Testing
Sender | bar: 2021-10-01 to 2022-02-11
Receiver | bar: 2021-10-01 to 2022-02-11
Phase-3
Pre- Work
|  | Tenneco | Access to Identified systems, wherever required | bar: 2021-09-10 to 2021-09-24
Design
|  | Tenneco | AS-IS Process, FS and TS, Field Mapping & Logic | bar: 2021-10-01 to 2021-10-15
|  | Tenneco and IBM | Design Meetings, TO-BE Process and Approval | bar: 2021-10-22 to 2021-11-12
|  | Tenneco | Identify Test Systems | bar: 2021-10-22 to 2021-11-12
|  | Tenneco and IBM | Finalize Unit Test Strategy | bar: 2021-10-22 to 2021-11-12
Build and Unit Testing
Sender | bar: 2021-11-12 to 2022-02-18
Receiver | bar: 2021-11-12 to 2022-02-18

## InScope Countries-Langs
· 41 Countries – 72,000 total employees / 8,000 contractors
· >10,000 Employees: USA
· 5,000 – 9,999 Employees: Mexico, Germany, Poland, China, India
· 1,000 – 4,999 Employees: Brazil, Czech Republic, France, Belgium, Spain, United Kingdom, South Africa
· 100 – 999 Employees: Italy, Russian Federation, Thailand, Romania, Argentina, Canada, Sweden, Hungary, South Korea, Japan, Australia
· <100 Employees: Portugal, Vietnam, Morocco, Singapore, Denmark, Philippines, Taiwan, Turkey, Ukraine, Egypt, Netherlands, Bulgaria, Croatia, Finland, Greece, Norway, Serbia and Montenegro
· 8Languages
· English, Spanish, German, Polish, Simplified Chinese, Portuguese, Czech, French

## EE Counts
S.No | Country | CW | Hourly | Salaried | Grand Total | Order by Employee Count | Payroll/Time | Pensioners
43 | USA | 1248 | 11733 | 4020 | 17001 | 1 | Yes
20 | India | 4975 | 5032 | 1326 | 11333 | 2 | Yes
23 | Mexico | 515 | 9418 | 1360 | 11293 | 3 | Yes
16 | Germany | 870 | 6812 | 2361 | 10043 | 4 | Yes | 4800-HPC | 2100-H1P(CA)
7 | China | 1913 | 4095 | 2188 | 8196 | 5 | Yes
28 | Poland | 627 | 5795 | 1172 | 7594 | 6 | Yes
4 | Brazil | 319 | 2343 | 481 | 3143 | 7 | Yes
11 | Czech Republic | 176 | 1505 | 315 | 1996 | 8 | Yes
15 | France | 162 | 1069 | 437 | 1668 | 9 | Yes
3 | Belgium | 67 | 1044 | 504 | 1615 | 10 | Yes
36 | Spain | 2 | 1224 | 301 | 1527 | 11 | Yes
34 | South Africa | 31 | 1026 | 260 | 1317 | 12 | Yes
42 | United Kingdom | 47 | 760 | 398 | 1205 | 13 | Yes
21 | Italy | 73 | 554 | 234 | 861 | 14 | No
39 | Thailand | 65 | 581 | 173 | 819 | 15 | No
31 | Russian Federation | 8 | 624 | 173 | 805 | 16 | No
1 | Argentina | 10 | 489 | 147 | 646 | 17 | No
30 | Romania | 4 | 352 | 276 | 632 | 18 | No
6 | Canada |  | 509 | 98 | 607 | 19 | Yes
19 | Hungary | 137 | 344 | 102 | 583 | 20 | Yes
37 | Sweden | 67 | 212 | 249 | 528 | 21 | Yes
35 | South Korea | 11 | 273 | 90 | 374 | 22 | No
22 | Japan | 118 | 93 | 129 | 340 | 23 | No
2 | Australia | 20 | 114 | 47 | 181 | 24 | No
24 | Morocco | 67 | 48 | 17 | 132 | 25 | No
29 | Portugal | 16 | 43 | 17 | 76 | 26 | Yes
44 | Vietnam | 2 | 44 | 17 | 63 | 27 | No
27 | Philippines | 16 |  | 10 | 26 | 28 | No
33 | Singapore |  |  | 21 | 21 | 29 | No
40 | Turkey | 5 |  | 9 | 14 | 30 | No
12 | Denmark | 1 | 5 | 3 | 9 | 31 | No
38 | Taiwan |  | 1 | 8 | 9 | 32 | No
41 | Ukraine |  |  | 8 | 8 | 33 | No
8 | Colombia |  |  | 4 | 4 | 34 | No
13 | Egypt |  |  | 4 | 4 | 35 | No
9 | Costa Rica |  |  | 2 | 2 | 36 | No
5 | Bulgaria |  |  | 1 | 1 | 37 | No
10 | Croatia |  |  | 1 | 1 | 38 | No
14 | Finland |  |  | 1 | 1 | 39 | No
17 | Greece |  |  | 1 | 1 | 40 | No
18 | Guatemala |  |  | 1 | 1 | 41 | No
25 | Netherlands |  |  | 1 | 1 | 42 | No
26 | Norway |  |  | 1 | 1 | 43 | No
32 | Serbia And Montenegro |  |  | 1 | 1 | 44 | No
| Grand Total | 11572 | 56142 | 16969 | 84683

## Complexity
Complexity | Count
Very High | 3
High | 13 | Total | 58
Medium | 17 | In-Scope | 48
Low | 15 | TBD | 10
Total In-Scope | 48

## Grading Key
Inbound / Outbound | In or Out | By nature, inbounds are more complex with more possible data issues
Country?
Data: Employee / Payroll / Both / Other |  | Business Area
Documents : FS or TS or Both Design
Field Mapping
Custom Infotype/Fields
If In, is Initial EE Record | Yes or No | By nature, establishing the initial EE record is more complex
Change Tracking | 1 – Full file | Out - The more specific the identification of specifically what needs to be set the greater the complexity and testing
2 – Any EE change, all data
3 – Each change, that table
4 – Only fields that have changed
Testability Concerns | Yes or No, if Yes give specifics | Out - Many downstream applications may not have a place to test, often alternate file handling is needed for testing only
In – Often the downstream applications cant create a file, at all, or that matches the testing database
Sequencing Importance | Yes or No, if Yes give specifics | Out – Does the receiving application have to receive in a specific action based order, often after an action in SF, other data is changed, at the interface run, the total of all changes are seen as one lump
Data Value Translation | Yes or No | Are translations needed to/from legacy values
D3 – where will mapping logic be housed, in SF or at interface, who should maintain
Total Files | # | Often one interface can have 2, 5, or 15 different files needed for various conditions, how many total files
File Transmit | File Mover or Point to Point | If point to point, what mechanism is in place (Web Service, ect)
Future Dated Rows | Send now or send later | Are future dated changes sent at time of changed, or need to be retained and sent when effective date is timely, retaining for later is more complex and harder to test
Timeliness | Batch (regardless of frequency) or Truly Realtime (or very short delay) | Does the integration need the changed data sent in real time? If so the tracking mechanisms are a different type of build and overlap considerations for the design are needed
Error Handling | Standard or Custom, if custom give specifics | If custom, are files or notifications sent to specific users or locations, maintenance and testability of these need to be considered
D4 – What is the standard policy for communicating execution and data issues
Existing Interface | Yes or No | New interfaces are higher risk and effort as there are not know SME’s and receiving application needs to built also in same time period
How Executed | Schedule or On-Demand | If on demand, by who and how. If end user, the access and controls need to be built in
Easiest Solution
Above Simple
Above Hard
Complex

## Interface List-Original
Business Units
Vendor/System | Interface Name | Middleware | File Format | In/Out | MP | RP | CA | PT | Division | SAP System | MPRP move to Employee Central | CAPT Move to Employee Central | Global | Comments | Target Systems | Country? | Data: Employee / Payroll / Both / Other | Documents : FS or TS or Both Design | Field Mapping | Custom Infotype/Fields | Initial EE Record?? | Change Tracking | Testability Concerns | Sequencing Importance | Data Value Translation | Total Files | File Transmit | Future Dated Rows | Timeliness | Error Handling | Existing Interface | How Executed | AS Comments
Active Directory | Active Directory | PI | text | Outbound | X | X | X |  | Both | H1P | yes | yes | Yes | yes = | 2 AD MPRP & CAPT Systems | All | Employee | Yes | Yes | Yes
Active Directory | Active Directory | PI | text | Inbound | X | X | X |  | Both | H1P | yes | yes | Yes | yes = Working Email ID ( Reserved across all systems ) SUBTY 0010 | 2 AD MPRP & CAPT Systems | All | Employee | Yes - USERID & EMAILID
Certify | Certify Census | EDI | text | Outbound |  | X |  |  | RP | H1P | yes | NA | No | no = ?? | Only for RP in US |  | Employee | Spec - Murali | [14 empty] | NA for CAPT as it is using CONCUR
SAP PTA (T&E) | Out of Pocket Expenses from PTA | EDI | text | Inbound |  | X |  |  | RP | H1P | no | NA | No | Inbound from PTA to H1P for out of pocket expense payment in Payroll. PTA receive this data from Certify
SAP PTA (T&E) | Travel and Entertainment Census | EDI | text | Outbound |  | X |  |  | RP | H1P | No |  | No | No |  |  | Employee + Mastercard details
Empyrean | Payroll Deduction | PI | text | Outbound | X | X |  |  | DRiV | H1P | no |  | No |  |  |  | Payroll
Empyrean | Demographic / Census | PI | text | Outbound | X | X |  |  | DRiV | H1P | no |  | No | The Census file also has information of Hours worked by employee. |  |  | Both
Empyrean | PII Empyrean | PI | text | Inbound | X | X |  |  | DRiV | H1P | no |  | No | This is Deduction amounts from Empyrean to SAP. Need to stay in SAP. |  |  | Payroll
Enablon | Enablon | EDI | text | Outbound | X | X |  |  | Both | H1P | yes | yes | Yes | EHS - Lisa Tet… ( Business Contact ) |  | All | Employee | SPEC - Murali
Equifax | Employee Verification/The Work Number, Unemployment Claims and WOTC/Work Opportunity Tax Credit |  | text | Outbound | X | X |  |  | DRiV | H1P | no |  | No |  |  |  | Both
Fidelity | Global Stock Option | PI | text | Outbound | X | X |  |  | Both | H1P | no | no | Yes | This is outbound for Stocks. Has Payroll data. |  |  | Both
Fidelity | Fidelity Payroll | PI | text | Outbound | X | X |  |  | DRiV | H1P | no |  | No |  |  |  | Payroll
Fidelity | Fidelity Census Salary | PI | text | Outbound | X | X |  |  | DRiV | H1P | No |  | No | Only US MPRP Salaried TBD, can be clubbed |  |  | Employee
Fidelity | Fidelity Census Hourly Thus Chk | PI | text | Outbound | X | X |  |  | DRiV | H1P | No |  | No | Hourly THU Paydate TBD |  |  | Employee
Fidelity | Fidelity Census Hourly Fri Chk | PI | text | Outbound | X | X |  |  | DRiV | H1P | No |  | No | Hourly Fri Chk TBD |  |  | Employee
Fidelity | Fidelity Loan | PI | text | Inbound | X | X |  |  | DRiV | H1P | no |  | No
Fidelity | Fidelity 401K | PI | text | Inbound | X | X |  |  | DRiV | H1P | no |  | No
iJET | Ijet | PI | text | Outbound | X | X |  |  | DRiV | H1P | yes | Yes | Yes | This is to Worldaware who sends travel advisory notifications to place they employee is travelling to. It has employee master data and can be moved. |  |  | Employee
Met Life | Met Life FMLA | PI | text | Outbound | X | X | X |  | Both | H1P | no | No, this has payroll data | No | Metlife manage FMLA for US employee. This has Payroll information and hours worked information to determine FMLA eligibility.
Met Life | Met Life Employee Eligible | PI | text | Outbound | X | X |  |  | DRiV | H1P | No |  | No
Met Life | Met Life Remittance | PI | text | Outbound | X | X |  |  | DRiV | H1P | no |  | No
Met Life | PII Met Life | PI | text | Inbound | X | X |  |  | DRiV | H1P | no |  | No
Peoplefluent | Compensation Mgt | NA | NA | Outbound |  |  |  |  | DRiV | H1P | no longer needed |  | Yes | Not in USE - Informed by Christine Fritz
Success Factors | User Directory | PI | text | Outbound | X | X |  |  | DRiV | H1P | will no longer be needed |  | Yes
Success Factors | Personal Information | PI | text | Outbound | X | X |  |  | DRiV | H1P | will no longer be needed |  | Yes
Success Factors | Background Information | PI | text | Outbound | X | X |  |  | DRiV | H1P | will no longer be needed |  | Yes
Success Factors | Position Management | PI | text | Outbound | X | X |  |  | DRiV | H1P | will no longer be needed
EC to SAP Master Data & Org Assignment Data H1P RP | Successfactors to SAP HR |  |  | Inbound |  |  |  |  | RP | H1P | new
EC to SAP Master Data & Org Assignment Data H1P RP | Successfactors to SAP HR |  |  | Inbound |  |  |  |  | CA | H1P | new | new
EC to SAP Master Data & Org Assignment Data H1P RP | Successfactors to SAP HR |  |  | Inbound |  |  |  |  | MP | VPC | new
EC to SAP Master Data & Org Assignment Data H1P RP | Successfactors to SAP HR |  |  | Inbound |  |  |  |  | PT | HPC | new | new
CFDI | Mexico Payroll CFDI Files | PI | xml | Outbound | X | X | X | X | Both | H1P & VPC | no | no | No
CFDI | Mexico Stamped CFDI Files | PI | xml | Inbound | X | X | X | X | Both | H1P & HPC | no | no | No
JPMC ACH | ACH File to JPMC Bank | EDI | text | Outbound | X | X |  |  | DRiV | H1P | no |  | No
JPMC Positive Pay | Check File to JPMC Bank | EDI | text | Outbound | X | X |  |  | DRiV | H1P | no |  | No
JPMC Card Data | JP Morgan T&E Card data | EDI | text | Inbound | X | X |  |  | DRiV | H1P | no |  | No
JPMC Acknowledgement | Positive Pay totals Acknowledgement from JPMC Bank | EDI | text to IDOC | Inbound | X | X |  |  | DRiV | H1P | no |  | No
JPMC Acknowledgement | Positive Pay Acknowledgement from JPMC Bank by each employee, | EDI | text to IDOC | Inbound | X | X |  |  | DRiV | H1P | no |  | No
JPMC Acknowledgement | ACH Pay Totals Acknowledgement from JPMC Bank | EDI | text to IDOC | Inbound | X | X |  |  | DRiV | H1P | no |  | No
JPMC Acknowledgement | ACH Pay Acknowledgement from JPMC Bank by each employee, | EDI | text to IDOC | Inbound | X | X |  |  | DRiV | H1P | no |  | No
Labor Distribution | Labor Distribution Time File - Kettering | EDI | text | Outbound |  | X |  |  | RP | H1P | no |  | No
Labor Distribution | Labor Distribution Time File - Paragould | EDI | text | Outbound |  | X |  |  | RP | H1P | no |  | No
Labor Distribution | Labor Distribution Time File - Hartwell | EDI | text | Outbound |  | X |  |  | RP | H1P | no |  | No
Labor Distribution | Labor Distribution Time File - Cambridge |  |  | Outbound |  |  |  |  | CA | H1P | no | No, this has time data | No
Global Headcount Reporting(GHC) | SAP HANA | PI | text | Outbound | X | X | X |  | Both | H1P | Yes | yes | Yes | SF-WFA |  |  |  | Info - Jeroen
Oracle | ENGR ORACLE | PI | text | Outbound |  | X |  |  | RP | H1P | Yes? | No | Yes | Employee Master data to Oracle engineering system in EMEA and APAC |  |  |  | Info - Jeroen
FIORI | FIORI US TIMESHEET | EDI | text | Outbound | X | X | X |  | DRiV | H1P | No | No |  | Employee data related to Fiori Timesheet
BEMON006 (AS/400 St Truiden) | Personal work schedule | EDI | text | Outbound |  | X |  |  | RP | H1P | No |  | No | There is a project in analysis phase for replacing AS400.
FIORI | FIORI NEWHIRES | EDI | text | Outbound | X | X |  |  | DRiV | H1P | Yes? | Yes | Yes | Employee census data for New Hires. - For Provisioning access in the Fiori Gateway(PGW-SAP System) - Need to discuss with GRC ( Corina & Colin Tosh)
GRC | [13 empty] | Need to discuss with GRC ( Corina Smith MPRP & Colin Tosh CAPT)
ESS SharePoint | Phone Fax Upload to SAP | EDI | text | Inbound | X | X | X |  | Both | H1P | will no longer be needed |  |  | No Longer needed, Update happens in EC
Kronos Demographic File | Motorparts US Kronos Time Management system | PI | text | Outbound | X |  |  |  | DRiV | H1P | No | No | No
Kronos Time File | Motorparts US Payroll Time Data to SAP | PI | text | Inbound | X |  |  | X | DRiV | H1P | no | No | No
Motorparts Payroll GL File | Payroll GL File to Motorparts Non SAP ERP locations | PI | text | Outbound | X |  |  |  | DRiV | H1P | no | No | No
Concur | Employee master data for concur |  | text to IDOC | Email | X |  | X |  | MP | H1P | yes | yes | Yes | 2 Concur Systems
CIS Database | Employee masterdata to CIS Lotusnotes DB |  |  | Outbound |  |  |  |  | CA | H1P | No | No | No
ADP Brazil | Employee and time data to ADP for Brazil payroll | PI | IDOC | Outbound |  | X | X |  | Both | H1P | Yes? | no | no
Platinum | China Payroll Platinum Interface | PI | text | Outbound |  | X | X |  | Both | H1P | No | No | No | Platinium EE Number is determined by H1P
ADP Pass Thru | Employee Master data |  |  | Outbound |  |  | X |  | CAPT | H1P | No | No
ADP Pass Back | Employee master data, address, phone numbers |  |  | Inbound |  |  | X |  | CAPT | H1P | no | No |  | Will the data be updated in EC for CA and PT instead of H1P and ADP?
ADP | EPIP | PI | IDOC | Outbound |  |  | X |  | CA | H1P | No | No
Cornerstone | Employee Master Data |  |  | Outbound |  |  |  | X | CAPT | H1P& HPC | No | No |  | SAP sends data to Cornerstone. Analyze the data feed from Cornerstone to other systems. Can they be moved to EC?
KDR | Skills Matrix Gdansk | [6 empty] | X | PT | HPC |  | No? | No
Various | FiCo Posting | [5 empty] | X | X | CAPT | HPC |  | No - Has Payroll Data | No
Various | Bank files | [6 empty] | X | CAPT | HPC |  | No - Has Payroll Data | No
RLP | 5x Controlling files, | [6 empty] | X | CAPT | HPC |  | No | No | Maybe in future phase
Kaba | Time & Attendance system | [6 empty] | X | CAPT | HPC |  | No needs EE Groupings and card nos | Yes | Stay in SAP
Kronos | Aguascalientes time system | [6 empty] | X | PT | HPC |  | No needs EE Groupings and card nos | No | Stay in SAP
BiBinet | BiBinet time system Gdansk | [6 empty] | X | PT | HPC |  | No needs EE Groupings and card nos | No | Stay in SAP
RCP | Gorzyce Time System | [6 empty] | X | PT | HPC |  | No needs EE Groupings and card nos | No | Stay in SAP
BDE | Nuremberg/Stadtallendorf Time system | [6 empty] | X | PT | HPC |  | No needs EE Groupings and card nos | No | Stay in SAP
ATOSS | Nuremberg/Wiesbaden EE planning | [6 empty] | X | PT | HPC |  | No needs time data | No | Stay in SAP
ATOSS | GVS time System | [6 empty] | X | PT | HPC |  | No needs time data | No | Stay in SAP
HPC <- >H1P | Employee Master data interface to H1P |  |  | Outbound |  |  |  | X | PT | HPC |  | Interface will nolonger be required | Yes | Stay in SAP - Supervisor ( 1% cross company/Country )
Portugal | Master Data only in H1P | [5 empty] | X |  | CA | H1P | No | No | No
France | PT Interface to ADP | [5 empty] | X |  | CA | H1P | No | No | No
German | In SAP, Master data to TA2 IT0050 | [5 empty] | X |  | CA | H1P | No | No | No
Hungary | time only in SAP, payroll only sourced | [5 empty] | X |  | CA | H1P | No | No | No
Denmark | Outsourced, time ? | [5 empty] | X |  | CA | H1P | No | No | No
Russia | Master Data only in H1P | [5 empty] | X |  | CA | H1P | unsure | Will need to investigate more |  | Can we maintain the data in EC and transferred to Non-SAP Payroll System??
Korea | Master Data only in H1P | [5 empty] | X |  | CA | H1P | unsure | Will need to investigate more |  | Can we maintain the data in EC and transferred to Non-SAP Payroll System??
Japan | Master Data only in H1P | [5 empty] | X |  | CA | H1P | unsure | Will need to investigate more |  | Can we maintain the data in EC and transferred to Non-SAP Payroll System??
Brazil | ADP - Interface | [7 empty] | CA | H1P | No | Contains monthly pay data
Argentina | Master Data only in H1P | [5 empty] | X |  | CA |  |  | Will need to investigate more |  | Can we maintain the data in EC and transferred to Non-SAP Payroll System??
Koblank | Burschied Suggestion Scheme | [5 empty] | X |  | PT | HPC |  | No
Umantis | DE Training system | [6 empty] | X | PT | HPC |  | No
Germany Payroll | Elster | PI | XML | Outbound |  |  |  | X | PCAPT | VPC | no | No
VPC to H1P | Motorparts Employee master data to H1P | PI | IDOC | Outbound | X |  |  | X |  | VPC | No | No |  | Stay in SAP - Supervisor ( 1% cross company/Country )
Concur | Expense payments | PI | IDOC | Inbound |  |  | X | X | PT | HPC |  | No?? |  | DE and MX expenses paid via payroll
Hansalog | HR App | PI | IDOC to file | Both |  |  |  | X | PT | HPC |  | Yes?? | No | NEW - Friedberg HR system - project start in March
AEB Solutions | AEB - Terror profiling | PI | IDOC to file | Outbound |  |  |  | X | PT | HPC |  | Yes?? | No | NEW - Start to build ASAP - Wiesbaden
ivocoPro | No spec received yet | PI | IDOC to file | Outbound |  |  |  | X | PT | HPC |  | No?? | No | NEW - Burschied - Time punch data. To start ASAP
No needs EE Groupings and card nos